## How to use
How to use — D.fend Fin Crime Forum Workback Plan
'Dashboard' tab
The dashboard gives a high-level summary of all activities on the 'Activities' tab: total activities, completed vs. outstanding tasks, progress by workstream, and outstanding tasks by owner. Use it to quickly gauge overall Forum readiness and spot areas needing attention.
'Gantt Chart' tab
A week-by-week view of when each workstream is active, from kickoff through the Forum date and post-event wrap-up. Use it for a quick visual of what should be running in any given week.
'Activities' tab
Term | Description
Workstream | Grouping of related activities by phase of the event (e.g., Survey Fielding & Insights, Venue and Catering Finalization).
Activity | A specific task that needs to be completed within a workstream (start with a verb).
What "Done" Looks Like | Clear definition of what successful completion of the activity looks like.
Dependencies | Other activity number(s) that must be complete first, and why.
Start / End Date | Planned start and end date for the activity (yyyy-mm-dd).
Duration | Auto-calculated from Start/End Date once both are filled in.
Actual End Date | The date the activity was actually completed — used to track slippage vs. plan.
Ownership | The person/role responsible for the activity. Keep the 'Dashboard' owner list (cells A26:A32) in sync with who's assigned.
Status | Select from the dropdown: Complete / In progress / --. Cells shade automatically (green = Complete, yellow = In progress).
'Team Coordination' tab
Day-of roles and responsibilities for the organizing team (registration desk, AV/tech, moderator support, etc.).
'Reference' tab
Quick links and notes for recurring event-logistics needs (registration platform, AV/IT support, signage, badge printing).

## Dashboard
D.fend Fin Crime Forum – Event Workback Dashboard
Forum Date: | 2026-11-13
Days to Forum:
Total Activities |  | Completed Activities |  | Outstanding Activities
Workstream Summary
Workstream | Total Activities | Completed | Outstanding
Survey Fielding & Insights
Agenda and Topic Finalization
Venue and Catering Finalization
Invitation & Registration Materials
Findings Deck & Presentation Materials
Pre-Event Planning
Outreach and Registration
Signage & Event Logistics
Event Execution Logistics
Day-of Roles
Day-of Event Execution
Post-Event Follow-Up
Outstanding Tasks by Owner
Owner | Total Activities | Completed | Outstanding
Project Lead
Research Lead
Deck Lead
Event Logistics Lead
Registration & Marketing Lead
Moderator / Presenter

## Gantt Chart
D.fend Fin Crime Forum – 10-Week Gantt (illustrative – confirm against Forum date)
Workstream | Wk 1 Aug 31 | Wk 2 Sep 07 | Wk 3 Sep 14 | Wk 4 Sep 21 | Wk 5 Sep 28 | Wk 6 Oct 05 | Wk 7 Oct 12 | Wk 8 Oct 19 | Wk 9 Oct 26 | Wk 10 Nov 02 | Wk 11 Nov 09
Survey Fielding & Insights
Agenda and Topic Finalization
Venue and Catering Finalization
Invitation & Registration Materials
Findings Deck & Presentation Materials
Pre-Event Planning
Outreach and Registration
Signage & Event Logistics
Event Execution Logistics
Day-of Roles
Day-of Event Execution
Post-Event Follow-Up
D.fend Forum | [10 empty] | ◆
Weeks are illustrative starting from an assumed kickoff of Aug 31, 2026 — shift all bars once the Forum date and survey launch date are confirmed.

## Activities
D.fend – Fin Crime Forum: Event Workback Plan
Action | Workstream | Activity (START WITH VERB) | What "Done" Looks Like | Dependencies | Start Date (yyyy-mm-dd) | End Date (yyyy-mm-dd) | Duration | Actual End Date (yyyy-mm-dd) | Ownership | Status (Complete/In progress) | Notes
1 | Survey Fielding & Insights | Finalize survey instrument and GLG screener logic | Approved questionnaire ready for fielding | None | 2026-08-24 | 2026-08-28 |  | 2026-08-28 | Research Lead | Complete
2 | Survey Fielding & Insights | Launch survey fielding via GLG | Live survey link distributed to GLG panel | #1
3 | Survey Fielding & Insights | Monitor fielding progress and quota fill (Week 1) | Daily response/quota tracking in place | #2
4 | Survey Fielding & Insights | Mid-field quota check and rebalancing (Week 2) | Quota gaps identified and outreach adjusted | #3
5 | Survey Fielding & Insights | Final quota push and close fielding (Week 3) | Fielding closed with quotas met | #4
6 | Survey Fielding & Insights | Milestone 1 – Survey Fielding Closed | Closed, validated dataset ready for tabulation
7 | Survey Fielding & Insights | Tabulate results and build cross-tabs | Cross-tabbed results by segment (banking/insurance, region) | #6
8 | Survey Fielding & Insights | Populate findings into the storyboard deck | Draft findings deck complete | #7
9 | Survey Fielding & Insights | Milestone 2 – Survey Findings & Draft Deck Complete | First full draft of findings deck ready for review | #8
10 | Agenda and Topic Finalization | Discuss anticipated attendees and seniority targets with leadership | Defined attendee profile and attendance target | None
11 | Agenda and Topic Finalization | Draft Forum agenda informed by survey headline findings | Draft agenda mapped to the 5 research themes | #9
12 | Agenda and Topic Finalization | Review agenda and session structure with leadership | Incorporated leadership feedback into draft agenda | #11
13 | Agenda and Topic Finalization | Confirm keynote/panel/breakout topics and speakers | Confirmed session owners and formats | #12
14 | Agenda and Topic Finalization | Obtain leadership approval of final agenda | Finalized and approved agenda for distribution | #13
15 | Agenda and Topic Finalization | Milestone 3 – Agenda & Attendee Targets Confirmed | Confirmed attendee targets and approved agenda | #14
16 | Venue and Catering Finalization | Check venue availability (Deloitte office or external) for target date | Identified venue options and confirmed availability | None
17 | Venue and Catering Finalization | Confirm date and venue with leadership | Aligned with leadership on venue availability | #16
18 | Venue and Catering Finalization | Book event space and reserve registration area | Secured venue booking and registration table reservation | #17
19 | Venue and Catering Finalization | Estimate food and beverage budget | Developed catering budget based on attendance estimate | #10
20 | Venue and Catering Finalization | Obtain catering budget approval | Approved catering budget for planning purposes | #19
21 | Venue and Catering Finalization | Arrange catering services | Confirmed menu, service times, and order | #20
22 | Venue and Catering Finalization | Milestone 4 – Venue & Catering Confirmed | Confirmed venue, registration area, and catering | #21
23 | Invitation & Registration Materials | Send placeholder calendar hold to target attendee list | Distributed placeholder invite with confirmed date/time | #18
24 | Invitation & Registration Materials | Draft invitation (agenda, venue, RSVP link) | Prepared invitation with agenda and venue details | #14, #18
25 | Invitation & Registration Materials | Review invitation with leadership | Incorporated leadership feedback into invitation | #24
26 | Invitation & Registration Materials | Send invitation to full attendee/prospect list | Distributed invitation to organizers, leadership, and attendees | #25
27 | Invitation & Registration Materials | Draft thank-you / post-event follow-up email template | Prepared thank-you email including agenda recap | None
28 | Invitation & Registration Materials | Milestone 5 – Invitation Materials Finalized | Finalized invitation and post-event email templates | #27
29 | Findings Deck & Presentation Materials | Apply Deloitte branding and finalize storyboard skeleton | Presentation template aligned to branding standards | #14
30 | Findings Deck & Presentation Materials | Share draft findings deck with slide owners/presenters | Assigned slide ownership and distributed materials | #8
31 | Findings Deck & Presentation Materials | QA review #1 – content flow, data accuracy, formatting | Verified content flow, accuracy, and branding compliance | #8
32 | Findings Deck & Presentation Materials | Review findings deck with leadership | Incorporated leadership feedback into deck | #31
33 | Findings Deck & Presentation Materials | Obtain leadership approval of final findings deck | Approved findings deck for Forum delivery | #32
34 | Findings Deck & Presentation Materials | Milestone 6 – Findings Deck Finalized | Finalized findings deck ready for rehearsal | #33
35 | Pre-Event Planning | Set up shared folder and supporting templates | Centralized workspace accessible to organizing team | None
36 | Pre-Event Planning | Create a Teams channel for the Forum organizing team | Established communication channel with all organizers added | None
37 | Pre-Event Planning | Schedule weekly organizing-team stand-ups | Scheduled recurring meetings and communicated expectations | None
38 | Outreach and Registration | Set up the registration link/tracker | Configured and tested registration platform | #17
39 | Outreach and Registration | Distribute registration link to attendee list | Sent registration link to intended attendees | #26, #38
40 | Outreach and Registration | Milestone 7 – Registration Opened | Opened attendee registration process | #39
41 | Outreach and Registration | Download registration report and reconcile against invite list | Generated report for reconciliation purposes | #38
42 | Outreach and Registration | Share registration status with leadership | Provided leadership with attendance trends | #41
43 | Outreach and Registration | Send reminder invites to outstanding attendees | Distributed reminders to all outstanding invitees | #42
44 | Outreach and Registration | Register external attendees per required process | Completed external-attendee registration requirements | #41
45 | Outreach and Registration | Milestone 8 – Registration Closed | Completed registration and reconciliation activities | #44
46 | Signage & Event Logistics | Draft event signage (agenda, welcome, sponsor recognition) | Prepared signage aligned to branding and venue requirements | #21
47 | Signage & Event Logistics | Approve event signage | Approved signage for production and event use | #46
48 | Signage & Event Logistics | Coordinate AV/IT and videoconferencing requirements | Confirmed technical requirements and event-day support | #18
49 | Signage & Event Logistics | Order name tags, lanyards, and badge holders | Ordered event materials and confirmed delivery | #43
50 | Event Execution Logistics | Confirm moderator(s) and panel speakers | Selected moderator(s) and communicated responsibilities | #14
51 | Event Execution Logistics | Prepare keynote/panel Q&A discussion questions | Developed and approved discussion questions | #34
52 | Event Execution Logistics | Conduct full dry run with presenters and panelists | Completed rehearsal covering timing, handoffs, and tech | #34, #50, #51
53 | Event Execution Logistics | Milestone 9 – Rehearsal & Materials Complete | Confirmed speaker readiness and materials | #52
54 | Day-of Roles | Assign day-of responsibilities (Team Coordination tab) | Documented and communicated event-day roles | #48
55 | Day-of Event Execution | Set up registration desk, signage, and badges | Registration area ready 30 minutes before doors open | #47, #54
56 | Day-of Event Execution | Complete final AV/tech checks | Verified presentation, AV, and videoconferencing equipment | #48
57 | Day-of Event Execution | Facilitate Forum sessions and breakouts | Delivered agenda as planned; captured key discussion points | #53
58 | Post-Event Follow-Up | Distribute thank-you email with findings deck attached | Distributed approved thank-you email and materials | #28, #57
59 | Post-Event Follow-Up | Prepare and distribute session summary / key takeaways | Distributed summary of discussions and next steps | #57
60 | Post-Event Follow-Up | Retrospective meeting with organizing team | Reviewed what went well, what didn't, and lessons learned | #57
61 | Post-Event Follow-Up | Update workback plan with lessons learned for next event | Workback plan updated for future Forum planning | #60
Legend: white cells = fill in as you plan/execute. Row 3 is a worked example. Status auto-shades from the dropdown in column K.

## Team Coordination
Day-of Team Coordination
Role | Quantity | What They Do | Assigned To
Logistics Team Lead | 1 | Overall day-of point of contact; coordinates venue, catering, and AV
Registration Desk | 2 | Check in attendees, distribute name tags and materials
AV/IT Support | 1 | Manage presentation, videoconferencing, and technical troubleshooting
Moderator | 1 | Runs the agenda, introduces speakers, keeps sessions on time
Time Keeper / Mic Runner | 1 | Signals time remaining to speakers; runs mic during Q&A
Slide Assistant | 1 | Advances slides and cues transitions for presenters
Note Taker | 1 | Captures key discussion points for the post-event summary
Attendee Flow / Elevator Coordinator | 1 | Directs attendees from entrance/elevator to event space

## Reference
Reference – Links & Notes
Activity | Link / Resource | Notes
Register external guests | [Internal registration/ServiceNow link]
AV / videoconferencing support | [Internal IT support request link] | Confirm needs at least 1 week before the Forum
Print name tags | [Internal print-service request link] | [Contact / lead-time note]
Order lanyards, badge holders, name trays | [Internal supplies request link] | Each name tray typically holds ~50 tags — confirm quantity
GLG survey fielding platform | [GLG project/portal link] | Primary channel for survey fielding status