## Slide 1
D.FEND – FIN CRIME FORUM
Fraud Landscape Survey — Workback Plan
Field-to-final path from survey launch to Forum-ready deck
Plan basis 3 weeks fielding (parallel skeleton build) → 1 week populate → 1 week review → final QA Dates illustrative — confirm launch date to lock calendar

## Slide 2
TIMELINE OVERVIEW
Six-week path: fielding and deck-build run in parallel, then populate, review, and final QA run sequentially
Aug 31
Sep 7
Sep 14
Sep 21
Sep 28
Oct 5
Kickoff & Launch
Track A — Survey Fielding (GLG)
Track B — Deck Skeleton Build
Populate Findings
Review & Revise
Final QA / Dry Run
Launch
Fielding open — monitor & manage quotas (GLG)
Build & refine deck skeleton
Tabulate + populate skeleton
Team + partner review
QA / dry run
D.fend Forum
[date TBD]
Fielding
Skeleton build
Populate
Review
QA / buffer
Weeks 1–3 run fielding and deck-build in parallel so the skeleton is ready to receive data the moment results close — eliminating dead time between fielding close and first draft.
D.fend – Fin Crime Forum | Fraud Landscape Survey | WORKBACK PLAN — DRAFT
Timeline
1

## Slide 3
DETAILED WORKBACK PLAN
Phase-by-phase tasks, timing, ownership, and deliverables from kickoff to Forum-ready deck
Phase | Timing | Key Tasks | Owner | Deliverable
Kickoff & Launch | Aug 31–Sep 1 | Finalize survey instrument & screener logic; confirm GLG quotas; launch fielding | [Project Lead] | Live survey link
Fielding — Wk 1 | Sep 1–5 | Monitor daily response volume & quota fill; QC early responses for data quality | [Research Lead] | Fielding status report
Skeleton Build — Wk 1 | Sep 1–5 | Build slide structure, section flow, governing-thought placeholders per theme | [Deck Lead] | Draft skeleton v1
Fielding — Wk 2 | Sep 8–12 | Mid-field check; rebalance quotas (banking/insurance, geography); chase gaps | [Research Lead] | Mid-field quota report
Skeleton Build — Wk 2 | Sep 8–12 | Finalize chart placeholders & categories per question; refine visual design | [Deck Lead] | Draft skeleton v2
Fielding — Wk 3 | Sep 15–19 | Final push to close remaining quotas; close fielding; validate & clean data | [Research Lead] | Closed, cleaned dataset
Skeleton Build — Wk 3 | Sep 15–19 | Finalize full skeleton incl. appendix/methodology; internal skeleton walkthrough | [Deck Lead] | Final skeleton, data-ready
Populate Findings — Wk 4 | Sep 22–26 | Tabulate & cross-tab results by segment; populate charts/stats; draft headlines | [Analytics + Deck Lead] | First full draft deck
Review & Revise — Wk 5 | Sep 29–Oct 3 | Internal team review; incorporate feedback; partner/leadership sign-off | [Full Team + Partner] | Reviewed near-final deck
Final QA & Dry Run | Oct 5–7 | Proofread & formatting QA; dry-run presentation; final sign-off | [Project Lead] | Forum-ready deck
D.fend Forum | [TBD] | Present survey findings to Forum audience | [Presenter] | —
D.fend – Fin Crime Forum | Fraud Landscape Survey | WORKBACK PLAN — DRAFT
Detailed Plan
2