## How to use
How to use
Dashboard' tab
The dashboard provides a high-level summary of all activities from the Activities tab. It displays: Total number of activities Number of completed and outstanding tasks Progress by workstream Outstanding tasks by owner Use the dashboard to quickly understand overall event readiness and identify areas that require attention.
Activities' tab
Terms | Description
Activities | The full list of tasks required to plan and execute the event
Workstream | Grouping of related activities by phase of the event (e.g., Pre-Event Planning, Logistics, Day-of)
Activity | A specific task that needs to be completed within a workstream
What "Done" looks like | Clear definition of what successful completion of the activity looks like
Due Date | The deadline by which the activity should be completed
Ownership | The assigned individual responsible for completing the activity. Update 'Dashboard' tab cells 20–29 to ensure owners are correctly linked
Status | When activity has been completed, indicate as complete

## Dashboard
Event Workback Plan Dashboard
Event Date: | 2026-08-26
Event Countdown | 1
Total Tasks |  | Completed Tasks |  | Outstanding Tasks
43 |  | 2 |  | 41
Workstream Summary | 4.651%
Workstream | Total Activities | Completed Activities | Outstanding Activities
Pre-Event Planning | 7 | 2 | 5
Outreach & Registration | 8 | 0 | 8
Pre-Event Logistics | 8 | 0 | 8
1 Week Prior Event Planning | 10 | 0 | 10
Day-of Event Execution | 6 | 0 | 6
Post-Event Follow-Up | 4 | 0 | 4
Outstanding Tasks by Owner
Owner | Total Activities | Completed Activities | Outstanding Activities
Owner 1 | 3 | 1 | 2
Owner 2 | 1 | 1 | 0
Owner 3 | 1 | 0 | 1
Owner 4 | 0 | 0 | 0
Owner 5 | 0 | 0 | 0
Owner 6 | 0 | 0 | 0
Owner 7 | 0 | 0 | 0
Owner 8 | 0 | 0 | 0
Owner 9 | 0 | 0 | 0
Owner 10 | 0 | 0 | 0

## Gantt Chart
10 Weeks
4 weeks | Agenda

## ACTIVITIES NEW
Event Workback Plan
Action | Workstream | Activity (START WITH VERB) | What "Done" Looks Like | Dependencies | Estimated Time Taken (Start to Finish: ~10 weeks) | Start Date (year-mm-dd) | End Date (year-mm-dd) | Duration | Actual End Date (year-mm-dd) | Ownership | Status (Complete/In Progress) | Notes
1 | Agenda and Topic Finalization | Receive event request from leadership | Email receieved from leadership on event objective and estimated venue date | None
2 | Agenda and Topic Finalization | Discuss anticipated attendees | Defined attendee profile and attendance target | None
3 | Agenda and Topic Finalization | Discuss whether the event will be organized with an external partner | Confirmed participation of an external partner and expected contribution | None
4 | Agenda and Topic Finalization | If working with external partners, clarify roles, responsibilities, and expectations | Documented agreed partner responsibilities, attendee targets and speaking roles | None
5 | Agenda and Topic Finalization | Discuss the detailed event topic and agenda with leadership (Lisa C., Kevin L., etc.) | Aligned event objectives, discussion topics, session structure, and duration | None
6 | Agenda and Topic Finalization | Draft the event topic and agenda based on leadership input | Completed draft agenda including objectives, topics, speakers, and timings | #5 – Leadership alignment on event objectives and discussion topics is required before drafting the agenda
7 | Agenda and Topic Finalization | Review the event topic and agenda with leadership (Stanley C., etc.) | Incorporated leadership feedback into the draft agenda
8 | Agenda and Topic Finalization | Obtain leadership approval of the event topic and agenda (Lisa C., Kevin L., etc.) | Finalized and approved the event agenda for distribution
9 | Agenda and Topic Finalization | Milestone 1 – Attendee Count and Agenda Confirmed | Confirmed attendee targets and approved agenda
10 | Room and Catering Finalization | Check room availability (Deloitte or external venue) for the proposed event date | Identified venue options and confirmed availability | #8 – Approved event duration are needed before evaluating venue options
11 | Room and Catering Finalization | Confirm date availability with leadership (Lisa C., Kevin L., etc.) | Aligned with leadership on venue availability | #10 – Available venue options should be reviewed before finalizing the event date
12 | Room and Catering Finalization | Book the event space (conference room and social space) and reserve a registration table in the lobby | Secured venue booking and registration table reservation
13 | Room and Catering Finalization | Estimate the food and beverage budget for the event | Developed catering budget based on attendance estimates and event format | #2, #10 – Attendance estimates drive catering quantities, and the event date and format affect catering requirements and pricing
14 | Room and Catering Finalization | Share the food and beverage budget with leadership for approval | Approved catering budget for event planning purposes
15 | Room and Catering Finalization | Arrange catering services | Confirmed menu selections, service times, attendee counts, and catering order | #14 – Budget approval is required before catering services can be confirmed
16 | Room and Catering Finalization | Milestone 2 – Room Booking and Catering Confirmed | Confirmed venue, registration table, and catering arrangements
17 | Invitation Material Finalization | Send a placeholder calendar (date, time) invite to Deloitte leadership and the organizing team | Distributed placeholder calendar invite with confirmed date and time | #12 – The event date should be confirmed before holding attendees' calendars
18 | Invitation Material Finalization | Draft the calendar invitation, including event details and agenda | Prepared calendar invitation with approved agenda, venue details, and attendee instructions | #8, #12 – The agenda should be approved and venue details confirmed before draft inivitation email
19 | Invitation Material Finalization | Review the calendar invitation with leadership (Stanley C., etc.) | Incorporated leadership feedback into the calendar invitation
20 | Invitation Material Finalization | Send the calendar invitation to the organizing team, external partners, and Deloitte leadership | Distributed calendar invitation to organizers, leadership, external partners, and attendees
21 | Invitation Material Finalization | Draft the thank-you email | Prepared thank-you email including event agenda and discussion topic | None
22 | Invitation Material Finalization | Review and obtain approval of the thank-you email from leadership (Stanley C., etc.) | Approved thank-you email for post-event distribution
23 | Invitation Material Finalization | Milestone 3 – Invitation Materials Finalized | Finalized invitation materials and post-event communications
24 | Material Finalization | Draft the presentation deck template | Created presentation template aligned with Deloitte branding standards | #8 – The agenda should be approved before presentation materials are developed
25 | Material Finalization | Share the draft presentation deck with designated slide owners | Assigned slide ownership and distributed presentation materials
26 | Material Finalization | Perform QA Review #1 of the presentation deck to ensure content flow and consistency | Verified content flow, formatting consistency, and branding compliance | #24 – Presentation content should be developed before quality assurance can be performed
27 | Material Finalization | Review presentation materials with leadership (Stanley C., etc.) | Incorporated leadership feedback into presentation materials
28 | Material Finalization | Obtain leadership approval of presentation materials (Lisa C., Kevin L., etc.) | Approved presentation materials for event delivery
29 | Material Finalization | Milestone 4 – Presentation Deck Finalized | Finalized presentation materials for event delivery
30 | Pre-Event Planning | Set up a shared folder and supporting templates | Created centralized workspace with folders, templates, and trackers accessible to event organizers | None
31 | Pre-Event Planning | Create a Teams group chat for Deloitte event organizers | Established communication channel and add all organizers. | None
32 | Pre-Event Planning | Schedule weekly stand-up meetings with event organizers | Scheduled recurring meetings and communicated attendance expectations | None
33 | Outreach and Registration | Set up the registration link (e.g., DU Tracker) | Configured and tested registration platform | None
34 | Outreach and Registration | Distribute the registration link to attendees | Sent registration link to intended attendees | #33 – The registration platform should be tested before distribution
35 | Outreach and Registration | Milestone 5 – Registration Opened | Opened attendee registration process
36 | Outreach and Registration | Download the attendee registration report from the registration platform | Generated attendee registration report for reconciliation purposes
37 | Outreach and Registration | Share the registration list with leadership (Lisa C., Kevin L., etc.) | Provided leadership with attendee registration status and attendance trends | #33 – Registration data should be available before sharing attendee status updates
38 | Outreach and Registration | Identify attendees included in the registration list who have not received the calendar invitation | Reconciled registration and invitation lists and identified attendance gaps
39 | Outreach and Registration | Send calendar invitations to outstanding attendees | Distributed invitations to all outstanding attendees
40 | Outreach and Registration | Register external attendees in ServiceNow | Completed ServiceNow registration requirements for external attendees | #37 – External attendees should be confirmed before ServiceNow registration is completed
41 | Outreach and Registration | Milestone 6 – Registration Completed | Completed attendee registration and invitation reconciliation activities
42 | Pre-Event Planning | Draft event signage | Prepared signage aligned with Deloitte branding standards and venue requirements | 89, #11 – Venue details and topic should be confirmed before signage is developed
43 | Pre-Event Planning | Review and obtain approval of event signage from leadership | Approved event signage for production and event use
44 | Pre-Event Planning | Coordinate IT support and videoconferencing requirements | Confirmed technical requirements, event-day support resources, and AV coverage | #11 – Venue selection should be confirmed before defining technology requirements
45 | Pre-Event Planning | Set up signage 30 minutes before the event and remove it 30 minutes after the event start time | Installed approved signage at designated event locations
46 | Pre-Event Planning | Milestone 7 – Signage Completed | Installed approved signage at designated event locations
47 | Event Execution Logistics | Confirm the Deloitte moderator | Selected moderator and communicated event responsibilities | #8 – Agenda and session structure should be finalized before selecting a moderator
48 | Event Execution Logistics | Prepare questions for the Q&A session | Developed and approved discussion questions to support event dialogue | #28 – Presentation materials should be finalized before preparing discussion questions
49 | Event Execution Logistics | Conduct a dry run with presenters and partners to confirm timing, handoffs, and speaking roles | Completed rehearsal covering timing, handoffs, speaker transitions, and technology validation | #28, #47, #48 – Presentation materials should be finalized, moderator confirmed, and Q&A content prepared before rehearsal
50 | Event Execution Logistics | Order lanyards, podium passes, and name trays | Ordered event materials and received order confirmations | #36 – Registration trends should be reviewed before determining material quantities
51 | Event Execution Logistics | Order name tags | Ordered name tags and confirmed delivery requirements | #36 – Registration trends should be reviewed before determining material quantities
52 |  | Milestone 8 - Event Execution Logistics | Confirmed speaker readiness, event materials, and rehearsal completion
53 | Day-of Roles | Assign event-day responsibilities in the Team Coordination tab | Documented and communicated event-day roles and responsibilities
54 | Day-of Event Execution | Collect and prepare lanyards | Prepared lanyards for attendee distribution and collection | #50, #51 – Lanyards should be received before they can be prepared
55 | Day-of Event Execution | Organize name tags alphabetically by last name | Arranged name tags alphabetically for attendee check-in | #54 – Name tags should be received before they can be organized
56 | Day-of Event Execution | Complete final technology and audiovisual checks | Verified functionality of presentation, audiovisual, and videoconferencing equipment
57 | Post-Event Follow-Up | Prepare and distribute meeting minutes | Distributed summary of key discussions, decisions, questions, and action items | Event Completed
58 | Post-Event Follow-Up | Send the thank-you email with the presentation attached | Distributed approved thank-you email and presentation materials to attendees | #22 – Email approval and event summary information should be available before distribution
59 | Post-Event Follow-Up | Retrospective meeting (with food) | Schedule a meeting with event organizers to review what went well, what did not, lessons learned, and next steps
60 | Post-Event Follow-Up | Update workback plan (tips/links) | Workback plan updated with any missing processes or improvements
Note on G2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: include start date, end date, duration, actual end date columns Reply: Included
Note on M2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: How do we note the dependencies?

## Activities (2)
Event Workback Plan
Action | Workstream | Activity (START WITH VERB) |  | What "Done" Looks Like | Dependencies | Estimated Time Taken (Start to Finish: ~10 weeks) | Start Date (year-mm-dd) | End Date (year-mm-dd) | Duration | Actual End Date (year-mm-dd) | Ownership | Status (Complete/In Progress) | Notes
Coordinate venue, and event with leaders prior to draft agenda ,topic anticipated audience
1 | Agenda and Topic Finalization | Confirm event format and key logistics | Milestone (budget - people coming, food we need, venue at deloitte or outside) (room - how many people), registration (how many people) | Event scope is fully defined, including confirmed date, target number of attendees, number and type of speakers, and total event duration | N/A | ~ 1 Week | 2026-07-20 | 2026-07-22 | 2 |  | Owner 1 | Complete
2 | Agenda and Topic Finalization | Draft budget | Budget -> leader input -> execute orders | Estimated budget covering venue, catering, and additional event materials | #1 - Budget estimates depend on the event format, attendance targets, and logistics requirements. |  | 2026-07-22 | 2026-07-25 | 3 |  | Owner 3 | In progress
3 | Pre-Event Planning | Set up shared folder and templates | Agenda -> set up place holders for organizing team + external partner and deloitte leadership | Centralized folder created with clear subfolders (e.g., outreach, logistics, materials) and trackers/templates accessible to all team members | N/A | ~ 1 Day |  |  | 0 |  | Owner 2 | Complete
4 | Pre-Event Planning | Send internal invite with key dates and placeholders |  | Send meeting invite to organizing team. Internal calendar placeholders for the event | N/A |  |  |  | 0 |  | Owner 1
5 | Pre-Event Planning | Create group chat on Teams for Deloitte event organizers |  | Teams chat created with all event organizers added | N/A |  |  |  | 0 |  | Owner 1
6 | Pre-Event Planning | Schedule weekly stand up calls with event organizers |  | Confirm tasks has been completed, and next steps | N/A |  |  |  | 0
7 | Pre-Event Planning | If working with vendor, clarify responsibilities and expectations | move before milestone event (before finalized agenda) | Vendor roles, attendee targets, and responsibilities clearly agreed | #1, #3 - Event objectives and budget constraints should be understood before engaging vendors. | ~ 1 Week |  |  | 0
8 | Outreach & Registration | Update Internal attendee coordination |  | Identify target attendees, align with partners/leaders, and finalize the internal outreach list. | N/A | On going |  |  | 0
9 | Outreach & Registration | External attendee coordination (if applicable) |  | Coordinate with the vendor to identify, review, and finalize the external attendee list. | #7 - Vendor responsibilities and attendee expectations must be agreed upon before coordinating outreach. |  |  |  | 0
10 | Agenda and Topic finalization | Draft Agenda |  | Draft agenda including the event objectives, session topics, timings | N/A | ~ 2 Week |  |  | 0
11 | Agenda and Topic finalization | Review and approval of the agenda |  | Draft agenda approved by leadership with feedback incorporated | N/A |  |  |  | 0
12 | Agenda and Topic finalization | Draft calendar invite |  | Calendar invite drafted with approved event details, agenda, date, time, venue and attendees instruction | N/A | ~ 1 Week |  |  | 0
13 | Agenda and Topic finalization | Send calendar invite |  | Invite distributed to attendees, with successful delivery confirmed | #11, #12 - Calendar invite and agenda must be finalized before distribution. |  |  |  | 0
14 | Outreach & Registration | Track registrations | Set up tracker (i.e., DU tracker) -> collect excel [ASK RILEY] -> send partner and leadership latest list (dates on when its sent out, T-1,T-3 etc.) | Tracker is up to date with confirmed attendees and follow-ups | #13 - Registration tracking begins once invitations are sent. | On going |  |  | 0
15 | Agenda and Topic finalization | Confirm catering |  | Food and drinks scheduled and ready 15 minutes before the designated serving time | #14 - Catering requirements depend on expected attendance. | On going |  |  | 0
16 | Agenda and Topic finalization | Book event space, Book room for food and beverage |  | Main room booked with seating layout (pods) and request for lanyard box for attendees to drop their lanyards after event | #1 - Venue requirements depend on approved event format and attendance targets. | ~ 2 Days |  |  | 0
17 | Agenda and Topic finalization |  |  | Rooms booked for cocktail/dinner hours, request set up 15min prior to scheduled time | #7 - Food and beverage orders depend on attendance estimates. |  |  |  | 0
18 | Pre-Event Logistics | Prepare draft signage |  | Signage draft in line with Deloitte standards | N/A | ~1 Week |  |  | 0
| Pre-Event Logistics | Review and approval of signage with leadership |  | Signage approved by leadership and IT | N/A
19 | Pre-Event Logistics | Coordinate IT support (videoconferencing capabilities) |  | IT confirmed to support AV and arrive 30min before event start time | #16 - IT requirements depend on the selected venue and event format. |  |  |  | 0
20 | Pre-Event Logistics | Signage (30min before and 30min after event start) |  | Signage placed 30min before registration opens and 30min after event start time | N/A |  |  |  | 0
21 | Pre-Event Logistics | Book registration table | Put all bookings together | Lobby registration table requested and confirmed | N/A |  |  |  | 0
22 | Agenda and Topic finalization | Draft and assign presentation materials to appropriate individual |  | Draft presentation materials completed, with each slide assigned to the appropriate individual for content development and review. | N/A |  |  |  | 0
Review and approval of presentation materials with leadership (Stanley etc.)
23 | 1 Week Prior Event Planning | Review and approval of presentation materials with leadership (Lisa, Kevin etc.) |  | Presentation materials reviewed by leadership, feedback incorporated, and final approval received for presentation at the event. | #22 - Completion of the presentation materials | ~ 2 Week |  |  | 0
24 | 1 Week Prior Event Planning | Review Materials (Final QA) |  | Confirm slide materials has consistent formatting | #22 - Completion of the presentation materials |  |  |  | 0
25 | 1 Week Prior Event Planning | Follow up partners for attendees | Sending excel attendees | Follow up with partner to complete and confirm the attendees | N/A | ~ 1 Week |  |  | 0
26 | Event Execution Logistics | Confirm Deloitte moderator |  | Select 1 or 2 individual as a moderator to introduce speakers | N/A |  |  |  | 0
27 | Event Execution Logistics | Prepare questions for Q&A |  | Set of 12 approved questions ready to guide discussion | N/A |  |  |  | 0
28 | Event Execution Logistics | Do a dry run with partners (handoffs, how long each speak etc.) | show materials, during the meeting the timekeeper will give you 5min signage for remaining, speaking order | Full dry run with speakers and moderators completed with timing and transitions confirmed | #23, #25 – Materials, speaker assignments, and Q&A topics must be finalized before rehearsal. |  |  |  | 0
29 | Event Execution Logistics | Place order for lanyards, podium pass, name trays |  | Confirm and share the confirmation email with the team. Order 10 extra lanyards | #14 - Attendance estimates are needed to determine quantities. | On going |  |  | 0
30 | Event Execution Logistics | Place order for name tags |  | Confirm and share the confirmation email with the team. Order 10 blank name tags | #14 - Attendance estimates are needed to determine quantities. |  |  |  | 0
31 | Event Execution Logistics | Draft 'thank you' email - moved up | Once agenda is finalized | Draft 'thank you' email including the key discussion topics | N/A | ~ 3 Days |  |  | 0
32 | Event Execution Logistics | Review and approval of 'thank you' email - moved up |  | Draft 'thank you' email approved by leadership with feedback incorporated | N/A |  |  |  | 0
33 | Event Execution Logistics | Assign note takers for meeting summary (Q&A) |  | Draft summary of questions and answers during the presentation | N/A | ~ 1 Day |  |  | 0
34 | Day of roles | Attendee Flow Coordinator (if necessary) |  | Escort attendees from one room to another | N/A |  |  |  | 0
35 | Day of roles | Timekeeper (align signage with speakers) |  | Provide a heads-up when speakers have 5 minutes left. Confirm with speakers the signal that will be used | N/A |  |  |  | 0
36 | Day of roles | Registration table (1x: guide guest, 1x check in, 1x event floor guiding to room) |  | Prepare name tags in trays and arrange them in alphabetical order (by last name); 1x guide guests from the registration table to the elevators, 1x check in attendees (attach name tags to lanyards), 1x floor guide to escort attendees to the room | N/A |  |  |  | 0
37 | Day-of Event Execution | Collect lanyards (have a box on the floor of the conference - optional |  | Collect all lanyards at the end of the event | N/A |  |  |  | 0
| Day-of Event Execution | Check name tags (arrange in alphabetical order -last name)
38 | Day-of Event Execution | Tech check |  | 1 hour prior to start, confirm all tech is working (slides, microphones, etc.) | N/A |  |  |  | 0
39 | Post-Event Follow-Up | Meeting minutes |  | Draft summary of questions and answers during the presentation | N/A |  |  |  | 0
40 | Post-Event Follow-Up | Send 'thank you' email with presentation attached |  | Thank you' email distributed to attendees, with successful delivery confirmed | #32 - Final approval must be completed first. |  |  |  | 0
41 | Post-Event Follow-Up | Retrospective meeting (w/ food) |  | Schedule a meeting with event organizers to review what went well, what did not, lessons learned, and next steps | N/A | ~ 1 Day |  |  | 0
42 | Post-Event Follow-Up | Update workback plan (tips/links) |  | Workback plan updated with any missing processes or improvements | N/A |  |  |  | 0
Formulas:
Duration = DAYS([End Date (year-mm-dd)],[Start Date (year-mm-dd)])
Note on H2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: include start date, end date, duration, actual end date columns Reply: Included
Note on N2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: How do we note the dependencies?
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Part of this exercise is to show how far out we need to conduct the planning. how can we show that? for instance, it almost looks like i can run this at the same time as the event or at worst a week before?
Note on E11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This one should be separated- there is an internal coordination effort and if applicable, an external attendee coordination with the vendor Reply: Separated into internal attendee coordination and external attendee coordination(if applicable)
Note on C36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: does this include review / approval cycles with leaders? Reply: I will break it down into 1)draft ‘thank you’ email 2) review and approval of ‘thank you’ email 3) send ‘thank you’ email

## Team Coordination
Role | Quantity | What they do | * Roles we need on the day of
Logistic Team Leader
IT support person
Catering person
Elevator Runners + Attendee flow coordinator | 1
Registration booth | 2 | 1 guide guest, 1 check in quest
Time keeper + Mic runner | 1 | sign during meeting
Moderator
Slide Assistant
Note Taker |  | for meeting summary

## OLD Activities
Event Workback Plan
Action | Workstream | Activity | What "Done" Looks Like | Dependencies | Estimated Time Taken (Start to Finish: ~10 weeks) | Start Date (year-mm-dd) | End Date (year-mm-dd) | Duration | Actual End Date (year-mm-dd) | Ownership | Status (Complete/In Progress) | Notes
Coordinate venue, and event with leaders prior to draft agenda ,topic anticipated audience
1 | Pre-Event Planning | Confirm event format and key logistics | Event scope is fully defined, including confirmed date, target number of attendees, number and type of speakers, and total event duration | N/A | ~ 1 Week | 2026-07-20 | 2026-07-22 | 2 |  | Owner 1 | Complete
2 | Pre-Event Planning | Draft budget | Estimated budget covering venue, catering, and additional event materials | #1 - Budget estimates depend on the event format, attendance targets, and logistics requirements. |  | 2026-07-22 | 2026-07-25 | 3 |  | Owner 3 | In progress
3 | Pre-Event Planning | Set up shared folder and templates | Centralized folder created with clear subfolders (e.g., outreach, logistics, materials) and trackers/templates accessible to all team members | N/A | ~ 1 Day |  |  | 0 |  | Owner 2 | Complete
4 | Pre-Event Planning | Send internal invite with key dates and placeholders | Send meeting invite to organizing team. Internal calendar placeholders for the event | N/A |  |  |  | 0 |  | Owner 1
5 | Pre-Event Planning | Group chat on Teams for Deloitte event organizers | Teams chat created with all event organizers added | N/A |  |  |  | 0 |  | Owner 1
6 | Pre-Event Planning | Schedule weekly stand up calls with event organizers | Confirm tasks has been completed, and next steps | N/A |  |  |  | 0
7 | Pre-Event Planning | If working with vendor, clarify responsibilities and expectations | Vendor roles, attendee targets, and responsibilities clearly agreed | #1, #3 - Event objectives and budget constraints should be understood before engaging vendors. | ~ 1 Week |  |  | 0
8 | Outreach & Registration | Update Internal attendee coordination | Identify target attendees, align with partners/leaders, and finalize the internal outreach list. | N/A | On going |  |  | 0
9 | Outreach & Registration | External attendee coordination (if applicable) | Coordinate with the vendor to identify, review, and finalize the external attendee list. | #7 - Vendor responsibilities and attendee expectations must be agreed upon before coordinating outreach. |  |  |  | 0
10 | Outreach & Registration | Draft Agenda | Draft agenda including the event objectives, session topics, timings | N/A | ~ 2 Week |  |  | 0
11 | Outreach & Registration | Review and approval of the agenda | Draft agenda approved by leadership with feedback incorporated | N/A |  |  |  | 0
12 | Outreach & Registration | Draft calendar invite | Calendar invite drafted with approved event details, agenda, date, time, venue and attendees instruction | N/A | ~ 1 Week |  |  | 0
13 | Outreach & Registration | Send calendar invite | Invite distributed to attendees, with successful delivery confirmed | #11, #12 - Calendar invite and agenda must be finalized before distribution. |  |  |  | 0
14 | Outreach & Registration | Track registrations | Tracker is up to date with confirmed attendees and follow-ups | #13 - Registration tracking begins once invitations are sent. | On going |  |  | 0
15 | Outreach & Registration | Confirm catering | Food and drinks scheduled and ready 15 minutes before the designated serving time | #14 - Catering requirements depend on expected attendance. | On going |  |  | 0
16 | Pre-Event Logistics | Book event space | Main room booked with seating layout (pods) and request for lanyard box for attendees to drop their lanyards after event | #1 - Venue requirements depend on approved event format and attendance targets. | ~ 2 Days |  |  | 0
17 | Pre-Event Logistics | Book room for food and beverage | Rooms booked for cocktail/dinner hours, request set up 15min prior to scheduled time | #7 - Food and beverage orders depend on attendance estimates. |  |  |  | 0
18 | Pre-Event Logistics | Prepare draft signage | Signage draft in line with Deloitte standards | N/A | ~1 Week |  |  | 0
| Pre-Event Logistics | Review and approval of signage with leadership | Signage approved by leadership and IT | N/A
19 | Pre-Event Logistics | Coordinate IT support (videoconferencing capabilities) | IT confirmed to support AV and arrive 30min before event start time | #16 - IT requirements depend on the selected venue and event format. |  |  |  | 0
20 | Pre-Event Logistics | Signage (30min before and 30min after event start) | Signage placed 30min before registration opens and 30min after event start time | N/A |  |  |  | 0
21 | Pre-Event Logistics | Book registration table | Lobby registration table requested and confirmed | N/A |  |  |  | 0
22 | Pre-Event Logistics | Draft and assign presentation materials to appropriate individual | Draft presentation materials completed, with each slide assigned to the appropriate individual for content development and review. | N/A |  |  |  | 0
23 | 1 Week Prior Event Planning | Review and approval of presentation materials with leadership | Presentation materials reviewed by leadership, feedback incorporated, and final approval received for presentation at the event. | #22 - Completion of the presentation materials | ~ 2 Week |  |  | 0
24 | 1 Week Prior Event Planning | Review Materials (Final QA) | Confirm slide materials has consistent formatting | #22 - Completion of the presentation materials |  |  |  | 0
25 | 1 Week Prior Event Planning | Follow up partners for attendees | Follow up with partner to complete and confirm the attendees | N/A | ~ 1 Week |  |  | 0
26 | 1 Week Prior Event Planning | Confirm Deloitte moderator | Select 1 or 2 individual as a moderator to introduce speakers | N/A |  |  |  | 0
27 | 1 Week Prior Event Planning | Prepare questions for Q&A | Set of 12 approved questions ready to guide discussion | N/A |  |  |  | 0
28 | 1 Week Prior Event Planning | Do a dry run with partners (handoffs, how long each speak etc.) | Full dry run with speakers and moderators completed with timing and transitions confirmed | #23, #25 – Materials, speaker assignments, and Q&A topics must be finalized before rehearsal. |  |  |  | 0
29 | 1 Week Prior Event Planning | Place order for lanyards, podium pass, name trays | Confirm and share the confirmation email with the team. Order 10 extra lanyards | #14 - Attendance estimates are needed to determine quantities. | On going |  |  | 0
30 | 1 Week Prior Event Planning | Place order for name tags | Confirm and share the confirmation email with the team. Order 10 blank name tags | #14 - Attendance estimates are needed to determine quantities. |  |  |  | 0
31 | 1 Week Prior Event Planning | Draft 'thank you' email | Draft 'thank you' email including the key discussion topics | N/A | ~ 3 Days |  |  | 0
32 | 1 Week Prior Event Planning | Review and approval of 'thank you' email | Draft 'thank you' email approved by leadership with feedback incorporated | N/A |  |  |  | 0
33 | Day-of Event Execution | Assign note takers for meeting summary (Q&A) | Draft summary of questions and answers during the presentation | N/A | ~ 1 Day |  |  | 0
34 | Day-of Event Execution | Attendee Flow Coordinator (if necessary) | Escort attendees from one room to another | N/A |  |  |  | 0
35 | Day-of Event Execution | Timekeeper (align signage with speakers) | Provide a heads-up when speakers have 5 minutes left. Confirm with speakers the signal that will be used | N/A |  |  |  | 0
36 | Day-of Event Execution | Registration table (1x: guide guest, 1x check in, 1x event floor guiding to room) | Prepare name tags in trays and arrange them in alphabetical order (by last name); 1x guide guests from the registration table to the elevators, 1x check in attendees (attach name tags to lanyards), 1x floor guide to escort attendees to the room | N/A |  |  |  | 0
37 | Day-of Event Execution | Collect lanyards (have a box on the floor of the conference - optional | Collect all lanyards at the end of the event | N/A |  |  |  | 0
38 | Day-of Event Execution | Tech check | 1 hour prior to start, confirm all tech is working (slides, microphones, etc.) | N/A |  |  |  | 0
39 | Post-Event Follow-Up | Meeting minutes | Draft summary of questions and answers during the presentation | N/A |  |  |  | 0
40 | Post-Event Follow-Up | Send 'thank you' email with presentation attached | Thank you' email distributed to attendees, with successful delivery confirmed | #32 - Final approval must be completed first. |  |  |  | 0
41 | Post-Event Follow-Up | Retrospective meeting (w/ food) | Schedule a meeting with event organizers to review what went well, what did not, lessons learned, and next steps | N/A | ~ 1 Day |  |  | 0
42 | Post-Event Follow-Up | Update workback plan (tips/links) | Workback plan updated with any missing processes or improvements | N/A |  |  |  | 0
Formulas:
Duration = DAYS([End Date (year-mm-dd)],[Start Date (year-mm-dd)])
Note on G2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: include start date, end date, duration, actual end date columns Reply: Included
Note on M2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: How do we note the dependencies?
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Part of this exercise is to show how far out we need to conduct the planning. how can we show that? for instance, it almost looks like i can run this at the same time as the event or at worst a week before?
Note on D11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This one should be separated- there is an internal coordination effort and if applicable, an external attendee coordination with the vendor Reply: Separated into internal attendee coordination and external attendee coordination(if applicable)
Note on C35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: does this include review / approval cycles with leaders? Reply: I will break it down into 1)draft ‘thank you’ email 2) review and approval of ‘thank you’ email 3) send ‘thank you’ email

## Activities
Event Workback Plan
Action | Workstream | Activity (START WITH VERB) |  | What "Done" Looks Like | Dependencies | Estimated Time Taken (Start to Finish: ~10 weeks) | Start Date (year-mm-dd) | End Date (year-mm-dd) | Duration | Actual End Date (year-mm-dd) | Ownership | Status (Complete/In Progress) | Notes
Coordinate event and venue with leadership prior
Check room availability
Coordinate venue, and event with leaders prior to draft agenda ,topic anticipated audience
1 | Agenda and Topic Finalization | Confirm event format and key logistics | Milestone (budget - people coming, food we need, venue at deloitte or outside) (room - how many people), registration (how many people) | Event scope is fully defined, including confirmed date, target number of attendees, number and type of speakers, and total event duration | N/A | ~ 1 Week | 2026-07-20 | 2026-07-22 | 2 |  | Owner 1 | Complete
2 | Agenda and Topic Finalization | Draft budget | Budget -> leader input -> execute orders | Estimated budget covering venue, catering, and additional event materials | #1 - Budget estimates depend on the event format, attendance targets, and logistics requirements. |  | 2026-07-22 | 2026-07-25 | 3 |  | Owner 3 | In progress
3 | Pre-Event Planning | Set up shared folder and templates | Agenda -> set up place holders for organizing team + external partner and deloitte leadership | Centralized folder created with clear subfolders (e.g., outreach, logistics, materials) and trackers/templates accessible to all team members | N/A | ~ 1 Day |  |  | 0 |  | Owner 2 | Complete
4 | Pre-Event Planning | Send internal invite with key dates and placeholders |  | Send meeting invite to organizing team. Internal calendar placeholders for the event | N/A |  |  |  | 0 |  | Owner 1
5 | Pre-Event Planning | Create group chat on Teams for Deloitte event organizers |  | Teams chat created with all event organizers added | N/A |  |  |  | 0 |  | Owner 1
6 | Pre-Event Planning | Schedule weekly stand up calls with event organizers |  | Confirm tasks has been completed, and next steps | N/A |  |  |  | 0
7 | Pre-Event Planning | If working with vendor, clarify responsibilities and expectations | move before milestone event (before finalized agenda) | Vendor roles, attendee targets, and responsibilities clearly agreed | #1, #3 - Event objectives and budget constraints should be understood before engaging vendors. | ~ 1 Week |  |  | 0
8 | Outreach & Registration | Update Internal attendee coordination |  | Identify target attendees, align with partners/leaders, and finalize the internal outreach list. | N/A | On going |  |  | 0
9 | Outreach & Registration | External attendee coordination (if applicable) |  | Coordinate with the vendor to identify, review, and finalize the external attendee list. | #7 - Vendor responsibilities and attendee expectations must be agreed upon before coordinating outreach. |  |  |  | 0
10 | Agenda and Topic finalization | Draft Agenda |  | Draft agenda including the event objectives, session topics, timings | N/A | ~ 2 Week |  |  | 0
11 | Agenda and Topic finalization | Review and approval of the agenda |  | Draft agenda approved by leadership with feedback incorporated | N/A |  |  |  | 0
12 | Agenda and Topic finalization | Draft calendar invite |  | Calendar invite drafted with approved event details, agenda, date, time, venue and attendees instruction | N/A | ~ 1 Week |  |  | 0
13 | Agenda and Topic finalization | Send calendar invite |  | Invite distributed to attendees, with successful delivery confirmed | #11, #12 - Calendar invite and agenda must be finalized before distribution. |  |  |  | 0
14 | Outreach & Registration | Track registrations | Set up tracker (i.e., DU tracker) -> collect excel [ASK RILEY] -> send partner and leadership latest list (dates on when its sent out, T-1,T-3 etc.) | Tracker is up to date with confirmed attendees and follow-ups | #13 - Registration tracking begins once invitations are sent. | On going |  |  | 0
15 | Agenda and Topic finalization | Confirm catering |  | Food and drinks scheduled and ready 15 minutes before the designated serving time | #14 - Catering requirements depend on expected attendance. | On going |  |  | 0
16 | Agenda and Topic finalization | Book event space, Book room for food and beverage |  | Main room booked with seating layout (pods) and request for lanyard box for attendees to drop their lanyards after event | #1 - Venue requirements depend on approved event format and attendance targets. | ~ 2 Days |  |  | 0
17 | Agenda and Topic finalization |  |  | Rooms booked for cocktail/dinner hours, request set up 15min prior to scheduled time | #7 - Food and beverage orders depend on attendance estimates. |  |  |  | 0
18 | Pre-Event Logistics | Prepare draft signage |  | Signage draft in line with Deloitte standards | N/A | ~1 Week |  |  | 0
| Pre-Event Logistics | Review and approval of signage with leadership |  | Signage approved by leadership and IT | N/A
19 | Pre-Event Logistics | Coordinate IT support (videoconferencing capabilities) |  | IT confirmed to support AV and arrive 30min before event start time | #16 - IT requirements depend on the selected venue and event format. |  |  |  | 0
20 | Pre-Event Logistics | Signage (30min before and 30min after event start) |  | Signage placed 30min before registration opens and 30min after event start time | N/A |  |  |  | 0
21 | Pre-Event Logistics | Book registration table | Put all bookings together | Lobby registration table requested and confirmed | N/A |  |  |  | 0
22 | Agenda and Topic finalization | Draft and assign presentation materials to appropriate individual |  | Draft presentation materials completed, with each slide assigned to the appropriate individual for content development and review. | N/A |  |  |  | 0
Review and approval of presentation materials with leadership (Stanley etc.)
23 | 1 Week Prior Event Planning | Review and approval of presentation materials with leadership (Lisa, Kevin etc.) |  | Presentation materials reviewed by leadership, feedback incorporated, and final approval received for presentation at the event. | #22 - Completion of the presentation materials | ~ 2 Week |  |  | 0
24 | 1 Week Prior Event Planning | Review Materials (Final QA) |  | Confirm slide materials has consistent formatting | #22 - Completion of the presentation materials |  |  |  | 0
25 | 1 Week Prior Event Planning | Follow up partners for attendees | Sending excel attendees | Follow up with partner to complete and confirm the attendees | N/A | ~ 1 Week |  |  | 0
26 | Event Execution Logistics | Confirm Deloitte moderator |  | Select 1 or 2 individual as a moderator to introduce speakers | N/A |  |  |  | 0
27 | Event Execution Logistics | Prepare questions for Q&A |  | Set of 12 approved questions ready to guide discussion | N/A |  |  |  | 0
28 | Event Execution Logistics | Do a dry run with partners (handoffs, how long each speak etc.) | show materials, during the meeting the timekeeper will give you 5min signage for remaining, speaking order | Full dry run with speakers and moderators completed with timing and transitions confirmed | #23, #25 – Materials, speaker assignments, and Q&A topics must be finalized before rehearsal. |  |  |  | 0
29 | Event Execution Logistics | Place order for lanyards, podium pass, name trays |  | Confirm and share the confirmation email with the team. Order 10 extra lanyards | #14 - Attendance estimates are needed to determine quantities. | On going |  |  | 0
30 | Event Execution Logistics | Place order for name tags |  | Confirm and share the confirmation email with the team. Order 10 blank name tags | #14 - Attendance estimates are needed to determine quantities. |  |  |  | 0
31 | Event Execution Logistics | Draft 'thank you' email | Once agenda is finalized | Draft 'thank you' email including the key discussion topics | N/A | ~ 3 Days |  |  | 0
32 | Event Execution Logistics | Review and approval of 'thank you' email |  | Draft 'thank you' email approved by leadership with feedback incorporated | N/A |  |  |  | 0
33 | Event Execution Logistics | Assign note takers for meeting summary (Q&A) |  | Draft summary of questions and answers during the presentation | N/A | ~ 1 Day |  |  | 0
34 | Day of roles | Attendee Flow Coordinator (if necessary) |  | Escort attendees from one room to another | N/A |  |  |  | 0
35 | Day of roles | Timekeeper (align signage with speakers) |  | Provide a heads-up when speakers have 5 minutes left. Confirm with speakers the signal that will be used | N/A |  |  |  | 0
36 | Day of roles | Registration table (1x: guide guest, 1x check in, 1x event floor guiding to room) |  | Prepare name tags in trays and arrange them in alphabetical order (by last name); 1x guide guests from the registration table to the elevators, 1x check in attendees (attach name tags to lanyards), 1x floor guide to escort attendees to the room | N/A |  |  |  | 0
37 | Day-of Event Execution | Collect lanyards (have a box on the floor of the conference - optional |  | Collect all lanyards at the end of the event | N/A |  |  |  | 0
| Day-of Event Execution | Check name tags (arrange in alphabetical order -last name)
38 | Day-of Event Execution | Tech check |  | 1 hour prior to start, confirm all tech is working (slides, microphones, etc.) | N/A |  |  |  | 0
39 | Post-Event Follow-Up | Meeting minutes |  | Draft summary of questions and answers during the presentation | N/A |  |  |  | 0
40 | Post-Event Follow-Up | Send 'thank you' email with presentation attached |  | Thank you' email distributed to attendees, with successful delivery confirmed | #32 - Final approval must be completed first. |  |  |  | 0
41 | Post-Event Follow-Up | Retrospective meeting (w/ food) |  | Schedule a meeting with event organizers to review what went well, what did not, lessons learned, and next steps | N/A | ~ 1 Day |  |  | 0
42 | Post-Event Follow-Up | Update workback plan (tips/links) |  | Workback plan updated with any missing processes or improvements | N/A |  |  |  | 0
Formulas:
Duration = DAYS([End Date (year-mm-dd)],[Start Date (year-mm-dd)])
Note on H2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: include start date, end date, duration, actual end date columns Reply: Included
Note on N2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: How do we note the dependencies?
Note on E6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Part of this exercise is to show how far out we need to conduct the planning. how can we show that? for instance, it almost looks like i can run this at the same time as the event or at worst a week before?
Note on E13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This one should be separated- there is an internal coordination effort and if applicable, an external attendee coordination with the vendor Reply: Separated into internal attendee coordination and external attendee coordination(if applicable)
Note on C38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: does this include review / approval cycles with leaders? Reply: I will break it down into 1)draft ‘thank you’ email 2) review and approval of ‘thank you’ email 3) send ‘thank you’ email

## OLD Activities (2)
Event Workback Plan
Action | Workstream | Activity (START WITH VERB) |  | What "Done" Looks Like | Dependencies | Estimated Time Taken (Start to Finish: ~10 weeks) | Start Date (year-mm-dd) | End Date (year-mm-dd) | Duration | Actual End Date (year-mm-dd) | Ownership | Status (Complete/In Progress) | Notes
Coordinate venue, and event with leaders prior to draft agenda ,topic anticipated audience
1 | Agenda and Topic finalization | Confirm event format and key logistics | Milestone (budget - people coming, food we need, venue at deloitte or outside) (room - how many people), registration (how many people) | Event scope is fully defined, including confirmed date, target number of attendees, number and type of speakers, and total event duration | N/A | ~ 1 Week | 2026-07-20 | 2026-07-22 | 2 |  | Owner 1 | Complete
2 | Agenda and Topic finalization | Draft budget | Budget -> leader input -> execute orders | Estimated budget covering venue, catering, and additional event materials | #1 - Budget estimates depend on the event format, attendance targets, and logistics requirements. |  | 2026-07-22 | 2026-07-25 | 3 |  | Owner 3 | In progress
3 | Pre-Event Planning | Set up shared folder and templates | Agenda -> set up place holders for organizing team + external partner and deloitte leadership | Centralized folder created with clear subfolders (e.g., outreach, logistics, materials) and trackers/templates accessible to all team members | N/A | ~ 1 Day |  |  | 0 |  | Owner 2 | Complete
4 | Pre-Event Planning | Send internal invite with key dates and placeholders |  | Send meeting invite to organizing team. Internal calendar placeholders for the event | N/A |  |  |  | 0 |  | Owner 1
5 | Pre-Event Planning | Create group chat on Teams for Deloitte event organizers |  | Teams chat created with all event organizers added | N/A |  |  |  | 0 |  | Owner 1
6 | Pre-Event Planning | Schedule weekly stand up calls with event organizers |  | Confirm tasks has been completed, and next steps | N/A |  |  |  | 0
7 | Pre-Event Planning | If working with vendor, clarify responsibilities and expectations | move before milestone event (before finalized agenda) | Vendor roles, attendee targets, and responsibilities clearly agreed | #1, #3 - Event objectives and budget constraints should be understood before engaging vendors. | ~ 1 Week |  |  | 0
8 | Outreach & Registration | Update Internal attendee coordination |  | Identify target attendees, align with partners/leaders, and finalize the internal outreach list. | N/A | On going |  |  | 0
9 | Outreach & Registration | External attendee coordination (if applicable) |  | Coordinate with the vendor to identify, review, and finalize the external attendee list. | #7 - Vendor responsibilities and attendee expectations must be agreed upon before coordinating outreach. |  |  |  | 0
10 | Agenda and Topic finalization | Draft Agenda |  | Draft agenda including the event objectives, session topics, timings | N/A | ~ 2 Week |  |  | 0
11 | Agenda and Topic finalization | Review and approval of the agenda |  | Draft agenda approved by leadership with feedback incorporated | N/A |  |  |  | 0
12 | Agenda and Topic finalization | Draft calendar invite |  | Calendar invite drafted with approved event details, agenda, date, time, venue and attendees instruction | N/A | ~ 1 Week |  |  | 0
13 | Agenda and Topic finalization | Send calendar invite |  | Invite distributed to attendees, with successful delivery confirmed | #11, #12 - Calendar invite and agenda must be finalized before distribution. |  |  |  | 0
14 | Outreach & Registration | Track registrations | Set up tracker (i.e., DU tracker) -> collect excel [ASK RILEY] -> send partner and leadership latest list (dates on when its sent out, T-1,T-3 etc.) | Tracker is up to date with confirmed attendees and follow-ups | #13 - Registration tracking begins once invitations are sent. | On going |  |  | 0
15 | Agenda and Topic finalization | Confirm catering |  | Food and drinks scheduled and ready 15 minutes before the designated serving time | #14 - Catering requirements depend on expected attendance. | On going |  |  | 0
16 | Agenda and Topic finalization | Book event space, Book room for food and beverage |  | Main room booked with seating layout (pods) and request for lanyard box for attendees to drop their lanyards after event | #1 - Venue requirements depend on approved event format and attendance targets. | ~ 2 Days |  |  | 0
17 | Agenda and Topic finalization |  |  | Rooms booked for cocktail/dinner hours, request set up 15min prior to scheduled time | #7 - Food and beverage orders depend on attendance estimates. |  |  |  | 0
18 | Pre-Event Logistics | Prepare draft signage |  | Signage draft in line with Deloitte standards | N/A | ~1 Week |  |  | 0
| Pre-Event Logistics | Review and approval of signage with leadership |  | Signage approved by leadership and IT | N/A
19 | Pre-Event Logistics | Coordinate IT support (videoconferencing capabilities) |  | IT confirmed to support AV and arrive 30min before event start time | #16 - IT requirements depend on the selected venue and event format. |  |  |  | 0
20 | Pre-Event Logistics | Signage (30min before and 30min after event start) |  | Signage placed 30min before registration opens and 30min after event start time | N/A |  |  |  | 0
21 | Pre-Event Logistics | Book registration table | Put all bookings together | Lobby registration table requested and confirmed | N/A |  |  |  | 0
22 | Agenda and Topic finalization | Draft and assign presentation materials to appropriate individual |  | Draft presentation materials completed, with each slide assigned to the appropriate individual for content development and review. | N/A |  |  |  | 0
Review and approval of presentation materials with leadership (Stanley etc.)
23 | 1 Week Prior Event Planning | Review and approval of presentation materials with leadership (Lisa, Kevin etc.) |  | Presentation materials reviewed by leadership, feedback incorporated, and final approval received for presentation at the event. | #22 - Completion of the presentation materials | ~ 2 Week |  |  | 0
24 | 1 Week Prior Event Planning | Review Materials (Final QA) |  | Confirm slide materials has consistent formatting | #22 - Completion of the presentation materials |  |  |  | 0
25 | 1 Week Prior Event Planning | Follow up partners for attendees | Sending excel attendees | Follow up with partner to complete and confirm the attendees | N/A | ~ 1 Week |  |  | 0
26 | Event Execution Logistics | Confirm Deloitte moderator |  | Select 1 or 2 individual as a moderator to introduce speakers | N/A |  |  |  | 0
27 | Event Execution Logistics | Prepare questions for Q&A |  | Set of 12 approved questions ready to guide discussion | N/A |  |  |  | 0
28 | Event Execution Logistics | Do a dry run with partners (handoffs, how long each speak etc.) | show materials, during the meeting the timekeeper will give you 5min signage for remaining, speaking order | Full dry run with speakers and moderators completed with timing and transitions confirmed | #23, #25 – Materials, speaker assignments, and Q&A topics must be finalized before rehearsal. |  |  |  | 0
29 | Event Execution Logistics | Place order for lanyards, podium pass, name trays |  | Confirm and share the confirmation email with the team. Order 10 extra lanyards | #14 - Attendance estimates are needed to determine quantities. | On going |  |  | 0
30 | Event Execution Logistics | Place order for name tags |  | Confirm and share the confirmation email with the team. Order 10 blank name tags | #14 - Attendance estimates are needed to determine quantities. |  |  |  | 0
31 | Event Execution Logistics | Draft 'thank you' email | Once agenda is finalized | Draft 'thank you' email including the key discussion topics | N/A | ~ 3 Days |  |  | 0
32 | Event Execution Logistics | Review and approval of 'thank you' email |  | Draft 'thank you' email approved by leadership with feedback incorporated | N/A |  |  |  | 0
33 | Event Execution Logistics | Assign note takers for meeting summary (Q&A) |  | Draft summary of questions and answers during the presentation | N/A | ~ 1 Day |  |  | 0
34 | Day of roles | Attendee Flow Coordinator (if necessary) |  | Escort attendees from one room to another | N/A |  |  |  | 0
35 | Day of roles | Timekeeper (align signage with speakers) |  | Provide a heads-up when speakers have 5 minutes left. Confirm with speakers the signal that will be used | N/A |  |  |  | 0
36 | Day of roles | Registration table (1x: guide guest, 1x check in, 1x event floor guiding to room) |  | Prepare name tags in trays and arrange them in alphabetical order (by last name); 1x guide guests from the registration table to the elevators, 1x check in attendees (attach name tags to lanyards), 1x floor guide to escort attendees to the room | N/A |  |  |  | 0
37 | Day-of Event Execution | Collect lanyards (have a box on the floor of the conference - optional |  | Collect all lanyards at the end of the event | N/A |  |  |  | 0
| Day-of Event Execution | Check name tags (arrange in alphabetical order -last name)
38 | Day-of Event Execution | Tech check |  | 1 hour prior to start, confirm all tech is working (slides, microphones, etc.) | N/A |  |  |  | 0
39 | Post-Event Follow-Up | Meeting minutes |  | Draft summary of questions and answers during the presentation | N/A |  |  |  | 0
40 | Post-Event Follow-Up | Send 'thank you' email with presentation attached |  | Thank you' email distributed to attendees, with successful delivery confirmed | #32 - Final approval must be completed first. |  |  |  | 0
41 | Post-Event Follow-Up | Retrospective meeting (w/ food) |  | Schedule a meeting with event organizers to review what went well, what did not, lessons learned, and next steps | N/A | ~ 1 Day |  |  | 0
42 | Post-Event Follow-Up | Update workback plan (tips/links) |  | Workback plan updated with any missing processes or improvements | N/A |  |  |  | 0
Formulas:
Duration = DAYS([End Date (year-mm-dd)],[Start Date (year-mm-dd)])
Note on H2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: include start date, end date, duration, actual end date columns Reply: Included
Note on N2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: How do we note the dependencies?
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Part of this exercise is to show how far out we need to conduct the planning. how can we show that? for instance, it almost looks like i can run this at the same time as the event or at worst a week before?
Note on E11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This one should be separated- there is an internal coordination effort and if applicable, an external attendee coordination with the vendor Reply: Separated into internal attendee coordination and external attendee coordination(if applicable)
Note on C36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: does this include review / approval cycles with leaders? Reply: I will break it down into 1)draft ‘thank you’ email 2) review and approval of ‘thank you’ email 3) send ‘thank you’ email

## Reference
Activities | Links | Notes
Register external guests | Catalog Item - MySupport
For videoconferencing capabilities and to arrange any other AV needs | Meeting and Conference On Site or Virtual IT Support - MySupport
Print name tags | Print Service Request - MySupport | - Request for 10 blank name tags -Contact gtaprintshop@deloitte.ca for any questions
Request for lanyards, podium pass, name trays | Lanyards and Other Pass Card Accessories - MySupport | - Lanyards, podium pass and name trays can only be picked up from the Security on the day of the event - Each name trays can hold 50 name tags - Request for 10 extra name tags